## Sheet1
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer | databaseAdministrator
A | Describe product |  | 16 | 40 | 80 | 1 | 0 | 0 | 0 | 0 | 0
B | Develop marketing strategy |  | 20 | 50 | 100 | 1 | 0 | 0 | 0 | 0 | 1
C | Design brochure | A | 10 | 20 | 40 | 0 | 1 | 0 | 0 | 0 | 0
D | Develop product prototype
D1 | Requirements analysis | A | 10 | 20 | 40 | 1 | 0 | 0 | 1 | 1 | 0
D2 | Software design | D1 | 20 | 40 | 80 | 1 | 1 | 1 | 1 | 1 | 1
D3 | System design | D1 | 15 | 30 | 60 | 1 | 0 | 1 | 0 | 1 | 1
D4 | Coding | D2, D3 | 40 | 120 | 240 | 0 | 1 | 1 | 1 | 1 | 0
D5 | Write documentation | D4 | 20 | 40 | 80 | 1 | 1 | 1 | 1 | 1 | 0
D6 | Unit testing | D4 | 15 | 30 | 60 | 0 | 1 | 1 | 1 | 1 | 0
D7 | System testing | D6 | 20 | 40 | 80 | 1 | 1 | 1 | 1 | 0 | 0
D8 | Package deliverables | D5, D7 | 5 | 10 | 20 | 1 | 0 | 0 | 0 | 0 | 0
E | Survey potential market | B, C | 20 | 40 | 80 | 1 | 0 | 0 | 0 | 0 | 0
F | Develop pricing plan | D8, E | 10 | 20 | 40 | 1 | 0 | 0 | 0 | 0 | 1
G | Develop implementation plan | A, D8 | 15 | 30 | 60 | 1 | 1 | 1 | 1 | 1 | 0
H | Write client proposal | F, G | 10 | 20 | 40 | 1 | 0 | 0 | 0 | 0 | 0
role | hourlyRate
projectManager | 46.22
frontendDeveloper | 52.35
backendDeveloper | 74.03
dataScientist | 60.4
dataEngineer | 60.12
databaseAdministrator | 63.16