## Best
BEST-CASE SCENARIO
Task ID | Task Name | Start Time | Duration | Predecessors
A | Describe product | 0 | 16
B | Develop marketing strategy | 0 | 20
C | Design brochure | 16 | 10 | A
D1 | Requirements analysis | 16 | 10
D2 | Software design | 26 | 20 | D1
D3 | System design | 26 | 15 | D1
D4 | Coding | 46 | 40 | D2, D3
D5 | Write documentation | 86 | 20 | D4
D6 | Unit testing | 86 | 15 | D4
D7 | System testing | 101 | 20 | D6
D8 | Package deliverables | 121 | 5 | D5, D7
E | Survey potential market | 26 | 20 | B, C
F | Develop pricing plan | 126 | 10 | D8, E
G | Develop implementation plan | 126 | 15 | A, D8
H | Write client proposal | 141 | 10 | F, G

## Expected
EXPECTED SCENARIO
Task ID | Task Name | Start Time | Duration | Predecessors
A | Describe product | 0 | 40
B | Develop marketing strategy | 0 | 50
C | Design brochure | 40 | 20 | A
D1 | Requirements analysis | 40 | 20
D2 | Software design | 60 | 40 | D1
D3 | System design | 60 | 30 | D1
D4 | Coding | 100 | 120 | D2, D3
D5 | Write documentation | 220 | 40 | D4
D6 | Unit testing | 220 | 30 | D4
D7 | System testing | 250 | 40 | D6
D8 | Package deliverables | 290 | 10 | D5, D7
E | Survey potential market | 60 | 40 | B, C
F | Develop pricing plan | 300 | 20 | D8, E
G | Develop implementation plan | 300 | 30 | A, D8
H | Write client proposal | 330 | 20 | F, G

## Worst
WORST-CASE SCENARIO
Task ID | Task Name | Start Time | Duration | Predecessors
A | Describe product | 0 | 80
B | Develop marketing strategy | 0 | 100
C | Design brochure | 80 | 40 | A
D1 | Requirements analysis | 80 | 40
D2 | Software design | 120 | 80 | D1
D3 | System design | 120 | 60 | D1
D4 | Coding | 200 | 240 | D2, D3
D5 | Write documentation | 440 | 80 | D4
D6 | Unit testing | 440 | 60 | D4
D7 | System testing | 500 | 80 | D6
D8 | Package deliverables | 580 | 20 | D5, D7
E | Survey potential market | 120 | 80 | B, C
F | Develop pricing plan | 600 | 40 | D8, E
G | Develop implementation plan | 600 | 60 | A, D8
H | Write client proposal | 660 | 40 | F, G